## Sheet1
ID | Risk event description and impact area | Impact Rating | Probability Rating | Risk Score | Risk Response Description | Trigger | If the impact to scope, cost, or customer is: | If the probability of the event occurring is: | Overall Risk Level is: | Risk Score
1 | Project schedule will exceed deadlines | 7 | 7 | 1 | keep on top of work to alleviate this | Slacking | High | High | High | 1
2 | team member's becoming unavailable due to illness or holiday | 2 | 4 | 2 | This becomes more of a risk when you rely on individuals for a particular skill. We are all competant with chosen technolgies so the risk is less. | n/a | High | Low | Medium/High | 2
3 | Risk chosen development tools can't handle workload | 4 | 1 | 4 | Find a suitable replacement if occurs | n/a | Low | High | Medium/Low | 3
4 | Risk project goes on a tanjent | 7 | 2 | 3 | Ensure requirements are clearly defined | inproper requirements - have to start guessing | Low | Low | Low | 4
5 | Risk to losing access to hardware | 1 | 1 | 4 | University provides loads of machines should we lose access to our personal devices | n/a